Grant Tracker Launch Readiness Plan April 2026 • Reference document for all pre-launch work

| ~300 grants live |  | 88 corporate partners |  | 5 sections to fix |  | ~1,500+ grant target |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

This document captures every remaining job needed before Grant Tracker launches publicly. Tasks are grouped by area and prioritised P0 (must-fix) through P3 (nice-to-have). P0 and P1 items should be completed before any public announcement. P2 items can be completed in the first 2–4 weeks post-soft-launch.

## 1 • Grant Data Quality

These are known gaps in the scraped_grants table identified during the audit in April 2026. Each one can be fixed directly in Supabase or via a targeted SQL update.

| Task | Owner | Effort | Priority |
| --- | --- | --- | --- |
| Metadata gaps — fix directly in Supabase |  |  |  |
| 118 grants missing impact sectors | Paul / Claude | 2–3 hrs | P1 — High |
| 16 grants missing location_tag | Claude | 30 mins | P1 — High |
| 9 grants missing funding_type | Claude | 30 mins | P1 — High |
| 1 grant past application deadline — deactivate or update | Claude | 5 mins | P0 — Critical |
| 11 grants with unchecked URLs — verify and update url_status | Claude | 1 hr | P1 — High |
| Scraper pipeline fixes |  |  |  |
| Fix P0 validation bug blocking 30–50 grants from activating | Claude (code) | 2 hrs | P0 — Critical |
| Remove 22 dead community foundation SOURCE_LABELS from codebase | Claude (code) | 30 mins | P1 — High |
| Fix Wellcome Trust crawler (crawls but returns 0 active grants) | Claude (code) | 2 hrs | P1 — High |
| Fix Lloyds Foundation crawler (crawls but returns 0 active) | Claude (code) | 2 hrs | P1 — High |
| Fix JRF (Joseph Rowntree Foundation) crawler | Claude (code) | 2 hrs | P1 — High |
| Fix Comic Relief crawler | Claude (code) | 2 hrs | P1 — High |
| Fix Nesta crawler | Claude (code) | 1 hr | P2 — Medium |
| Fix Rank Foundation crawler | Claude (code) | 1 hr | P2 — Medium |
| Fix Foyle Foundation crawler | Claude (code) | 1 hr | P2 — Medium |
| Fix Rosa UK crawler | Claude (code) | 1 hr | P2 — Medium |
| Fix GLA scraper (HTTP 403 error) | Claude (code) | 2 hrs | P2 — Medium |

## 2 • Grant Catalogue Depth

The catalogue currently holds ~300 grants. The target for broad sector coverage is 1,500–2,500. This is the single biggest competitive gap. 360Giving open data is the fastest win — it alone could add hundreds of verified grants within a day.

| Task | Owner | Effort | Priority |
| --- | --- | --- | --- |
| Quick wins (open data sources) |  |  |  |
| Ingest 360Giving open data — could add 200–500 grants in one batch | Claude (code) | 4 hrs | P0 — Critical |
| Ingest Grantnav / GrantNav API (uses 360Giving data) | Claude (code) | 2 hrs | P1 — High |
| Add UK Community Foundations umbrella feed | Claude (code) | 3 hrs | P1 — High |
| Missing high-priority trust sources |  |  |  |
| Add Arts Council England scraper (National Portfolio, Project Grants) | Claude (code) | 3 hrs | P1 — High |
| Add Creative Scotland / Arts Council Wales scrapers | Claude (code) | 2 hrs | P1 — High |
| Add Sport England / sportscotland scrapers | Claude (code) | 2 hrs | P1 — High |
| Add National Lottery Community Fund (Awards for All) — currently no feed | Claude (code) | 3 hrs | P1 — High |
| Add Tudor Trust scraper | Claude (code) | 1 hr | P2 — Medium |
| Add Paul Hamlyn Foundation scraper | Claude (code) | 1 hr | P2 — Medium |
| Add Esmee Fairbairn Foundation scraper | Claude (code) | 1 hr | P2 — Medium |
| Add Blagrave Trust scraper | Claude (code) | 1 hr | P2 — Medium |
| Add Stone Family Foundation scraper | Claude (code) | 1 hr | P2 — Medium |
| Add Guy’s & St Thomas’ Foundation scraper | Claude (code) | 1 hr | P2 — Medium |
| Corporate grant programmes (new catalogue category) |  |  |  |
| Add Lloyds Bank Foundation open grants page as scraped source | Claude (code) | 1 hr | P1 — High |
| Add BBC Children in Need as scraped source | Claude (code) | 1 hr | P1 — High |
| Add Google.org grants as scraped source | Claude (code) | 1 hr | P2 — Medium |
| Add Aviva Community Fund as scraped source | Claude (code) | 1 hr | P2 — Medium |
| Pro bono & Tech for Good intermediaries |  |  |  |
| Add LawWorks as grant/support source | Claude (code) | 30 mins | P2 — Medium |
| Add Charity Digital Exchange as tech support source | Claude (code) | 30 mins | P2 — Medium |
| Add Pilotlight as capacity-building source | Claude (code) | 30 mins | P2 — Medium |
| Add Advocate (Bar Pro Bono) as legal support source | Claude (code) | 30 mins | P3 — Nice |

## 3 • Website & Feature Gaps

Core pages are built and working. These are the remaining polish items and missing features that will affect user experience at launch.

| Task | Owner | Effort | Priority |
| --- | --- | --- | --- |
| Matching & search |  |  |  |
| Test matching algorithm across all 19 impact sectors end-to-end | Paul | 2 hrs | P0 — Critical |
| Verify grant size matching works for very small orgs (under £50k income) | Paul | 1 hr | P1 — High |
| Check Find Funding page — all 4 tabs (Grants, Programmes, Investment, In-Kind) | Paul | 1 hr | P1 — High |
| Confirm Programmes tab ‘Includes cash’ toggle filters correctly | Paul / Claude | 30 mins | P1 — High |
| Pipeline CRM |  |  |  |
| End-to-end test: add grant to pipeline, move through stages, mark won/lost | Paul | 1 hr | P1 — High |
| Verify deadline reminders appear correctly on dashboard | Paul | 30 mins | P1 — High |
| Check pipeline summary stats are accurate | Paul | 30 mins | P1 — High |
| Corporate Partners |  |  |  |
| Verify all 88 partners display correctly on /dashboard/corporate | Paul | 30 mins | P1 — High |
| Test profile matching — confirm scored results feel relevant | Paul | 30 mins | P1 — High |
| Test Save/Unsaved state persists across sessions | Paul | 15 mins | P1 — High |
| Onboarding & profile |  |  |  |
| Test full sign-up → profile setup → first match flow | Paul | 1 hr | P0 — Critical |
| Ensure profile completion prompt is shown to new users with empty profile | Paul / Claude | 30 mins | P1 — High |
| Add organisation type options for CIC and Social Enterprise (not just charity) | Claude (code) | 1 hr | P1 — High |
| Add income band selector if missing from profile form | Claude (code) | 1 hr | P1 — High |
| UI polish |  |  |  |
| Mobile responsiveness check across all dashboard pages | Paul / Claude | 2 hrs | P1 — High |
| Empty state screens — verify all load states and empty pipeline look good | Paul | 1 hr | P2 — Medium |
| Add sector filter to Find Funding page (currently no sector filter) | Claude (code) | 2 hrs | P2 — Medium |
| Add funder type filter to Find Funding (trust / corporate / public body) | Claude (code) | 2 hrs | P2 — Medium |
| Grant cards — confirm all display correctly with long titles/descriptions | Paul | 30 mins | P2 — Medium |
| Missing feature: Readiness Score / Match Briefing |  |  |  |
| Design Match Briefing — one-page summary per grant with approach notes | Paul (design) | 1 day | P2 — Medium |
| Build Match Briefing component and hook to grant detail page | Claude (code) | 4 hrs | P2 — Medium |
| Add Readiness Score to profile (how ready is this org to apply?) | Claude (code) | 4 hrs | P3 — Nice |

## 4 • Funder Intelligence

The funder_brief JSONB column exists on all grants. The foundational layer is in place. These tasks deepen the data and start building the longitudinal data moat that is Grant Tracker’s long-term defensibility.

| Task | Owner | Effort | Priority |
| --- | --- | --- | --- |
| Foundational data (launch-critical) |  |  |  |
| Audit which grants have populated funder_brief data vs empty | Claude | 1 hr | P1 — High |
| Populate funder_brief for the top 50 highest-traffic grants | Claude (research) | 4 hrs | P1 — High |
| Add typical_cycle field (rolling / annual / biannual) to all top-50 grants | Claude | 2 hrs | P1 — High |
| Add avg_award_size to top-50 grants where data is publicly available | Claude (research) | 2 hrs | P1 — High |
| Post-launch data deepening (Month 1–3) |  |  |  |
| Start logging historical award data for Wellcome, Lloyds, JRF, Comic Relief | Claude (research) | Ongoing | P2 — Medium |
| Add competitiveness score (oversubscribed / balanced / accessible) to top 100 | Claude (research) | 4 hrs | P2 — Medium |
| Add ‘currently open / closed / rolling’ status to grant cards in UI | Claude (code) | 2 hrs | P2 — Medium |
| Build funder profile pages (dedicated page per funder with all their grants) | Claude (code) | 1 day | P3 — Nice |
| Add decision timeline data to funder_brief (how long they take to decide) | Claude (research) | Ongoing | P3 — Nice |

## 5 • Business & Launch Readiness

Non-technical tasks needed before inviting paying users or making a public announcement.

| Task | Owner | Effort | Priority |
| --- | --- | --- | --- |
| Legal & compliance |  |  |  |
| Publish Privacy Policy page (GDPR compliant, UK ICO standard) | Paul | 2 hrs | P0 — Critical |
| Publish Terms of Service / Terms of Use page | Paul | 2 hrs | P0 — Critical |
| Cookie consent banner — verify it’s working and records consent | Paul / Claude | 1 hr | P0 — Critical |
| Register with ICO as a data controller if not already done | Paul | 30 mins | P0 — Critical |
| Payments & subscriptions |  |  |  |
| Set up Stripe (or equivalent) for £65/6-month and £115/year plans | Paul | 2 hrs | P0 — Critical |
| Build subscription management page (view plan, cancel, upgrade) | Claude (code) | 3 hrs | P0 — Critical |
| Implement paywall — grant detail locked after free tier limit | Claude (code) | 3 hrs | P0 — Critical |
| Free trial period decision — how many days / grants before paywall? | Paul (decision) | N/A | P0 — Critical |
| Add charity number field to registration — verify UK charity status | Claude (code) | 1 hr | P1 — High |
| Support & comms |  |  |  |
| Set up support email (e.g. hello@granttracker.co.uk) and auto-reply | Paul | 30 mins | P1 — High |
| Write welcome email sequence (signup → first match → 7-day tips) | Paul | 3 hrs | P1 — High |
| Create FAQ / help page with common user questions | Paul / Claude | 2 hrs | P1 — High |
| Set up basic error monitoring (Sentry or Vercel analytics) | Claude (code) | 1 hr | P1 — High |
| Go-to-market |  |  |  |
| Identify 10–20 beta users (sector contacts, networks, warm leads) | Paul | 1 day | P1 — High |
| Soft-launch sequence — email beta users, collect feedback | Paul | Ongoing | P1 — High |
| Set up waitlist / landing page for wider launch announcement | Claude (code) | 2 hrs | P2 — Medium |
| Reach out to Esme Verity / Considered Capital re: partnership | Paul | 1 hr | P2 — Medium |
| Submit to sector directories (NCVO, SCVO, Charity Finance Group) | Paul | 2 hrs | P2 — Medium |
| Draft launch blog post / LinkedIn announcement | Paul / Claude | 2 hrs | P2 — Medium |

## Launch Sequence Summary

Recommended order of work before going public:

| Phase | Focus | Key tasks |
| --- | --- | --- |
| 1 | Fix blockers (this week) | P0 items: deadline bug, validation bug, privacy/terms pages, Stripe setup, paywall, cookie consent, ICO registration |
| 2 | Data boost (week 1–2) | 360Giving ingest, fix top broken crawlers (Wellcome, Lloyds, JRF, Comic Relief), populate funder_brief top 50, fill metadata gaps |
| 3 | UX polish (week 2–3) | Full user journey test, mobile check, profile flow, sector/funder filters, empty states, welcome email sequence |
| 4 | Soft launch (week 3–4) | Invite 10–20 beta users, collect feedback, monitor errors, iterate on matching quality |
| 5 | Public launch (month 2) | Wider announcement, sector directories, Considered Capital intro, PR push, continue data deepening |

Grant Tracker  •  Launch Readiness Plan  •  April 2026  •  grant-tracker-kappa.vercel.app